## Test Cases
SmartEPT — Consolidated Test Suite · Sessions of 11–12 August 2026
MR-02 · companion to MR-01 · Part 1 = sessions 1–3 features (run on LIVE after deploy) · Part 2 = per-tenant licensing · Part 3 = licence change flows (Parts 2–3: local Laragon first, then P1s on live) · P1 must-pass before sign-off; any P1 Fail → Ejaz immediately
TC ID | Area | Priority | Title | Preconditions | Steps | Expected Result | Result | Tested By | Date | Notes
1A. Login, SMTP & forgot-password (S1, Product 22ed12e)
TC-1A01 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P1 | Seeded/unlocked super login works | Live deployed; super password unlocked via tinker and CHANGED | 1. Sign in at admin.smartept.com/admin as super@smartept.io with the new password | Login succeeds; Super Admin console loads (before the fix NO seeded login ever worked)
TC-1A02 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P1 | All seeded passwords changed | Live | 1. Attempt login for each seeded demo account with the old default 'password' | Every attempt FAILS — defaults were rotated after the double-hash fix
TC-1A03 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P1 | Global SMTP relay set and delivering | Super login; real SMTP credentials | 1. Ops → Email/SMTP → global section → save + Test | Test reports success; a real email arrives
TC-1A04 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P1 | Forgot-password end-to-end on live | Global SMTP set | 1. Console login card → Forgot password? → enter email → receive code → set new password 2. Sign in with it | OTP arrives by EMAIL (not log); reset works; login OK; audit shows PASSWORD_RESET_REQUESTED/COMPLETED
TC-1A05 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P2 | Company SMTP overrides global | A company with its own SMTP saved | 1. Save company SMTP (Ops card, company section) + Test 2. Trigger any mail for that company (e.g. forgot-password for its user) | Mail goes out via the COMPANY's SMTP/from; clearing host falls back to global
TC-1A06 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P2 | OTP guardrails | - | 1. Request OTP for an unknown email 2. Enter a wrong OTP 5 times 3. Use an expired (>10 min) code | Neutral response for unknown email (no probing); 5 attempts then blocked; expiry enforced
TC-1A07 | Login, SMTP & forgot-password (S1, Product 22ed12e) | P2 | Resend cooldown (S3, 389b8a0) | - | 1. Request OTP → button becomes 'Resend code (60s)' counting down 2. Try resending immediately via API | Button disabled for 60s; server also refuses early resends (throttle)
1B. Live bug verifications (S2, Product 1f6be35)
TC-1B01 | Live bug verifications (S2, Product 1f6be35) | P1 | Attendance derivation clean | Live deployed for 1+ day | 1. Check laravel.log for 'lessThan() on string' 2. Open Attendance for previously-affected employees | Zero new occurrences; attendance rows derive correctly (self-healed on next run)
TC-1B02 | Live bug verifications (S2, Product 1f6be35) | P1 | Rules screen saves CLOSE and BLOCK on both types | Admin login | 1. App & Web Rules → set a website rule action = CLOSE → Save 2. Set an application rule action = BLOCK → Save | Both save without error (previously 1265 'Data truncated' — ENUM strike four)
TC-1B03 | Live bug verifications (S2, Product 1f6be35) | P2 | Archive restore works | An archived (deleted) employee exists | 1. Employees → Archives → Restore | Restore completes; no 'Undefined array key new_employee_code'
1C. SEO & landing (S2, Central 4 commits)
TC-1C01 | SEO & landing (S2, Central 4 commits) | P1 | Sitemap is https-only allow-list | Live Central deployed | 1. Open https://smartept.com/sitemap.xml | Exactly 7 URLs, all https://smartept.com/... (/, contact, privacy, terms, refunds, security, system-requirements); no /buy, /pay, /client, /admin
TC-1C02 | SEO & landing (S2, Central 4 commits) | P2 | Canonicals + noindex headers | - | 1. View source of / and /privacy → canonical tag 2. curl -I https://smartept.com/client/login and /buy | Self-referencing https canonicals; workflow pages return X-Robots-Tag: noindex, follow
TC-1C03 | SEO & landing (S2, Central 4 commits) | P1 | GA4 flows on publish | GA4 id saved in Landing Editor | 1. Landing Editor → Publish → make live 2. View source of /, /privacy, /buy | Exactly ONE gtag install with the saved ID on each page; publishing twice never duplicates
TC-1C04 | SEO & landing (S2, Central 4 commits) | P2 | www redirects in one hop | Manual Nginx step applied on VPS | 1. curl -I for http://www., https://www., http://smartept.com | Each answers a SINGLE 301 to https://smartept.com/ (no chains, no 502)
1D. Branded URLs, licence auto-config & agent fix (S3)
TC-1D01 | Branded URLs, licence auto-config & agent fix (S3) | P1 | Agent works on a branded URL | Live product deployed | 1. Configure an agent with https://admin.smartept.com/khan 2. Sign in and sync | Login + sync succeed — /khan/api/* 308-bounces to /api/* with method+body preserved
TC-1D02 | Branded URLs, licence auto-config & agent fix (S3) | P1 | Licence validates with NO .env URL | Product server without SMARTEPT_LICENSE_URL | 1. Licence screen → Validate now | Phones https://smartept.com (Setting pushed by Central, else default) — no 'Central URL not configured' error
TC-1D03 | Branded URLs, licence auto-config & agent fix (S3) | P1 | Cross-company device re-registration (agent-500 fix) | A PC previously registered under company A | 1. Sign the agent in as an employee of company B on the same PC | Registration succeeds (no HTTP 500 / duplicate-key); device re-points to B; audit DEVICE_COMPANY_REASSIGNED; old company-A token dead (401)
TC-1D04 | Branded URLs, licence auto-config & agent fix (S3) | P2 | Payment History ledger (Central a055ed3) | Client with partial payments | 1. Central → client modal → Payment History | Every payment row with method/reference + 'Total received' matching the ledger
1E. Money spot-checks (S1 pricing — regression guard)
TC-1E01 | Money spot-checks (S1 pricing — regression guard) | P1 | Progressive lifetime price on /buy | Live bands (e.g. 15→₹15,000, 30→₹25,000) | 1. /buy → On-Premise → 15, 22, 30 users | 15=₹15,000; 30=₹25,000; 22 = interpolated between (~₹19,667 for the example bands); above last band = Custom Quote, never ₹0
TC-1E02 | Money spot-checks (S1 pricing — regression guard) | P2 | Admin delete guards (73888fc) | Super login; one paid order, one clean quote | 1. Try Delete on the PAID order 2. Delete the clean quote | Paid/money-bearing order: NO delete offered; clean quote deletes with confirmation; audit entries written
1F. Test-system health (S5 — run by a developer)
TC-1F01 | Test-system health (S5 — run by a developer) | P1 | Product full suite green | Repo at da11247+ | 1. cd C:\laragon\www\smartept && php artisan test | 0 failures (first healthy state since 19-Jul)
TC-1F02 | Test-system health (S5 — run by a developer) | P1 | Central full suite green | Repo at d28b56c+ | 1. cd C:\laragon\www\smartept-central && php artisan test | 56 passed / 342 assertions, 0 failures
TC-1F03 | Test-system health (S5 — run by a developer) | P2 | Provision endpoint tolerates omitted optional fields (2ca7dec) | Provisioning secret known (test env only) | 1. POST /api/provision with only external_tenant_id, company_name, admin_email | 201 — no 500 'Undefined array key timezone'
2A. Migration & data move — per-tenant licensing (S4)
TC-2A01 | Migration & data move — per-tenant licensing (S4) | P1 | Migration adds company_id and unique index cleanly | Product repo at 1fcb7f7; DB backed up | 1. php artisan migrate 2. DESCRIBE installation_licenses | Migration 2026_08_12_000400 runs without error; company_id column nullable BIGINT with UNIQUE index; no data lost
TC-2A02 | Migration & data move — per-tenant licensing (S4) | P1 | Khan key auto-moves to Khan's tenant row | Install slot holds Khan's key; exactly one AMETECS_SAAS company named 'Khan Incorporation' | 1. Run migration 2. SELECT company_id, license_key FROM installation_licenses | The existing row's company_id = Khan's company id; key, bundle, status preserved; no second row created
TC-2A03 | Migration & data move — per-tenant licensing (S4) | P2 | No-match safety (client-hosted shape) | DB where bundle company name matches no AMETECS_SAAS company | 1. Run migration on such a DB (e.g. local seeded) | Nothing moves: the licensed row keeps company_id NULL; behaviour identical to before
TC-2A04 | Migration & data move — per-tenant licensing (S4) | P2 | Ambiguity safety — two same-name SaaS companies | Two AMETECS_SAAS companies with identical name; install slot keyed | 1. Run migration | Move is skipped entirely (count != 1); no data changed
TC-2A05 | Migration & data move — per-tenant licensing (S4) | P3 | Migration down() reverses cleanly | Migration applied | 1. php artisan migrate:rollback --step=1 | Unique index and company_id column dropped; table intact
TC-2A06 | Migration & data move — per-tenant licensing (S4) | P1 | Fresh install slot after key move | Migration moved the key (Khan case) | 1. Open Licence screen as Super Admin 2. Check evaluation end date | A fresh empty install row exists (created on first access); shows EVALUATION with 7 days from creation; agents of non-SaaS companies keep working during window
2B. Licence resolution model — per-tenant licensing (S4)
TC-2B01 | Licence resolution model — per-tenant licensing (S4) | P1 | AMETECS_SAAS company governed by own row | SaaS company exists | 1. tinker: InstallationLicense::governing($saasCompany) | Returns row with company_id = that company; creates it empty on first call
TC-2B02 | Licence resolution model — per-tenant licensing (S4) | P1 | Non-SaaS company governed by install row | Company with deployment_model LAN/PRIVATE_CLOUD/HYBRID/null | 1. tinker: InstallationLicense::governing($company) | Returns the install-level row (company_id NULL) — pre-existing behaviour
TC-2B03 | Licence resolution model — per-tenant licensing (S4) | P2 | Null company (operator context) → install row | - | 1. tinker: InstallationLicense::governing(null) | Returns install-level row
TC-2B04 | Licence resolution model — per-tenant licensing (S4) | P2 | forCompany is idempotent | SaaS company | 1. Call InstallationLicense::forCompany($id) twice | Same row id both times; created_at unchanged (evaluation clock stable)
TC-2B05 | Licence resolution model — per-tenant licensing (S4) | P2 | Unique index blocks duplicate tenant rows | Tenant row exists | 1. Attempt raw INSERT with same company_id | MySQL rejects with duplicate-key error; app never creates duplicates (firstOrCreate)
TC-2B06 | Licence resolution model — per-tenant licensing (S4) | P3 | current() ignores tenant rows | Tenant rows exist | 1. tinker: InstallationLicense::current() | Returns only the company_id-NULL row, never a tenant's
2C. Licence screen by role — per-tenant licensing (S4)
TC-2C01 | Licence screen by role — per-tenant licensing (S4) | P1 | Cloud tenant admin sees own licence with scope line | Khan admin login (via /khan or /admin console) | 1. Sign in as Khan COMPANY_ADMIN 2. Open Licence | Scope row: 'This licence belongs to Khan Incorporation — issued and managed by SmartEPT Central'; Khan's masked key, plan, seats, expiry shown
TC-2C02 | Licence screen by role — per-tenant licensing (S4) | P1 | Tenant admin Save & validate writes own row only | Khan admin; valid key from Central | 1. Paste key, Save & validate 2. Check installation_licenses | Key stored on Khan's row (company_id set); install slot untouched; status ACTIVE after validation
TC-2C03 | Licence screen by role — per-tenant licensing (S4) | P2 | Tenant admin Validate now phones Central for own key | Khan row configured | 1. Click Validate now 2. Check last_checked_at on both rows | Khan row refreshed; install row last_checked_at unchanged
TC-2C04 | Licence screen by role — per-tenant licensing (S4) | P2 | Offline licence card hidden for cloud tenant admin | Khan admin on Licence screen | 1. Inspect page | 'Offline licence file' card not visible; fingerprint/import controls absent
TC-2C05 | Licence screen by role — per-tenant licensing (S4) | P1 | Offline .lic import API blocked for tenant scope | Khan admin token | 1. POST /api/license/import with any token | HTTP 403: 'Offline licence files apply to self-hosted servers…' message; no state change
TC-2C06 | Licence screen by role — per-tenant licensing (S4) | P2 | Super Admin licence screen shows install slot + pointer | super@smartept.io | 1. Open Licence | Install-level licence (or EVALUATION) shown; note 'Cloud tenants on this install carry their own licences — see the Tenants screen'
TC-2C07 | Licence screen by role — per-tenant licensing (S4) | P1 | Client-hosted admin behaviour unchanged (regression) | Local seeded install (LAN company); admin@ametecs.io | 1. Open Licence; save key; validate; import .lic | Identical to pre-change behaviour: install slot used, offline card visible and functional
TC-2C08 | Licence screen by role — per-tenant licensing (S4) | P2 | Device seats counted per scope | Khan row active with devices; other companies have devices too | 1. Khan admin Licence screen: seats line 2. Super admin Licence screen: seats line | Khan sees only Khan devices registered; install scope counts all devices on the box
2D. Provisioning key delivery (Central → Product) — per-tenant licensing (S4)
TC-2D01 | Provisioning key delivery (Central → Product) — per-tenant licensing (S4) | P1 | New cloud tenant fully licensed hands-free | Central 76ddf09 deployed; product 1fcb7f7 deployed; provisioning secret set | 1. In Central create/pay a cloud tenant (or Save an active one) 2. Open product Tenants screen | Company + admin created AND licence row ACTIVE with the tenant's key — no manual key entry anywhere
TC-2D02 | Provisioning key delivery (Central → Product) — per-tenant licensing (S4) | P1 | Re-provision re-pushes the key idempotently | Existing provisioned tenant | 1. Save the tenant again in Central 2. Check product row | Same key → row untouched (status/bundle preserved); changed key → row reset and revalidated
TC-2D03 | Provisioning key delivery (Central → Product) — per-tenant licensing (S4) | P2 | Provision without licence_key still works (legacy) | Tenant with no active licence | 1. Provision from Central | Company + admin created; no licence row forced; tenant runs on 7-day evaluation
TC-2D04 | Provisioning key delivery (Central → Product) — per-tenant licensing (S4) | P1 | Bad provisioning secret rejected | - | 1. POST /api/provision with wrong X-Provision-Secret | HTTP 401; nothing created or changed
TC-2D05 | Provisioning key delivery (Central → Product) — per-tenant licensing (S4) | P2 | Open my Console SSO unaffected | Provisioned tenant with console_url | 1. Central portal → Open my Console | Signed-in landing on branded console exactly as before
2E. Agent enforcement (EnsureLicensed) — per-tenant licensing (S4)
TC-2E01 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P1 | Licensed tenant agents sync normally | Khan licence ACTIVE | 1. Khan employee signs into agent; agent syncs | register-device / heartbeat / sync all pass
TC-2E02 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P1 | One tenant's dead licence never blocks another | Tenant X row set status=revoked (tinker); Khan ACTIVE | 1. X agent syncs 2. Khan agent syncs | X gets 403 LICENSE_BLOCKED (reason revoked); Khan completely unaffected
TC-2E03 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P1 | Expired within grace still syncs | Tenant row status=expired, expires_at within grace_days | 1. Agent sync | Traffic passes (grace window honoured per tenant)
TC-2E04 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P2 | Expired beyond grace blocks | Tenant row expired beyond grace | 1. Agent sync | 403 LICENSE_BLOCKED for that tenant only
TC-2E05 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P1 | Unlicensed SaaS tenant: 7-day evaluation then block | SaaS company with no key (fresh row) | 1. Sync during window 2. Set row created_at back 8 days (tinker); sync again | Passes during window; then 403 with reason evaluation_expired
TC-2E06 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P2 | Non-SaaS companies ride the install slot | Install slot ACTIVE (or in evaluation) | 1. Agent of LAN company syncs | Governed by install slot exactly as before the change
TC-2E07 | Agent enforcement (EnsureLicensed) — per-tenant licensing (S4) | P2 | Central unreachable → last verdict stands per tenant | Kill SMARTEPT_LICENSE_URL reachability (hosts file) on a test box | 1. Tenant with cached ACTIVE syncs | Sync continues; unreachable_since recorded; no false block
2F. Device seats per tenant — per-tenant licensing (S4)
TC-2F01 | Device seats per tenant — per-tenant licensing (S4) | P1 | Seat claimed against the employee's tenant key | Khan ACTIVE with free seats | 1. New Khan employee registers a device 2. Central licence page for Khan | Seat activates on Khan's licence at Central; devices_active increments for Khan only
TC-2F02 | Device seats per tenant — per-tenant licensing (S4) | P1 | Tenant seat limit blocks only that tenant | Tenant at device_limit | 1. One more device registers for that tenant 2. Khan (different tenant) registers a device | First gets 409 LICENSE_SEAT_BLOCKED device_limit_reached; Khan's registration succeeds
TC-2F03 | Device seats per tenant — per-tenant licensing (S4) | P2 | Unbind releases the tenant's seat | Bound device on Khan | 1. Devices → Unbind 2. Check Central seat count for Khan | Seat released on Khan's licence; token revoked; device blocked from re-registering until rebind
TC-2F04 | Device seats per tenant — per-tenant licensing (S4) | P2 | Rebind reclaims on the right licence | Unbound Khan device | 1. Devices → Rebind | Seat reclaimed against Khan's key; 409 with clear message if none free
TC-2F05 | Device seats per tenant — per-tenant licensing (S4) | P2 | Relieve employee releases every device per tenant | Khan employee with 2 devices | 1. Employees → Relieve (with reason) | Both seats released on Khan's licence; devices unbound; tokens revoked
2G. Storage reporting & governance — per-tenant licensing (S4)
TC-2G01 | Storage reporting & governance — per-tenant licensing (S4) | P1 | Per-tenant storage reported to Central | Two tenants with different storage footprints | 1. Validate each tenant (Tenants → Validate) 2. Central: storage_usages rows | Each tenant's storage_gb equals ITS OWN files only (not the whole box)
TC-2G02 | Storage reporting & governance — per-tenant licensing (S4) | P2 | Install row still reports whole-box storage | Install slot keyed (client-hosted case) | 1. Validate install licence | storage_gb = all evidence files on the server
TC-2G03 | Storage reporting & governance — per-tenant licensing (S4) | P1 | Tenant over quota pauses only that tenant's screenshots | Force tenant over 100% (Central storage governance) | 1. Validate tenant (pause flag returns) 2. That tenant's agent uploads screenshot 3. Khan agent uploads screenshot | Over-quota tenant gets 409 'Storage is full…'; Khan uploads fine; activity tracking continues for both
TC-2G04 | Storage reporting & governance — per-tenant licensing (S4) | P2 | Global storage pause still works (backward compat) | Set Setting storage_paused=1 | 1. Any agent uploads screenshot | 409 for all companies — install-wide switch honoured as before
TC-2G05 | Storage reporting & governance — per-tenant licensing (S4) | P2 | Storage bar colours & percentages on Tenants screen | Tenants at <70%, 70–89%, ≥90% of quota | 1. Open Tenants; compare used/quota/% | Bar green <70, amber 70–89, red ≥90; % = used/quota rounded; 'no quota' shown when unlimited
2H. Tenants screen (HOST) — per-tenant licensing (S4)
TC-2H01 | Tenants screen (HOST) — per-tenant licensing (S4) | P1 | Visible to Super Admin only | Accounts of each role | 1. Sign in as SUPER_ADMIN, COMPANY_ADMIN, HR_ADMIN, EMPLOYEE in turn | HOST → Tenants appears only for SUPER_ADMIN; other roles never see the section
TC-2H02 | Tenants screen (HOST) — per-tenant licensing (S4) | P1 | API gated server-side | Company admin token | 1. GET /api/tenants 2. POST /api/tenants/{id}/license/validate | Both 403 regardless of UI
TC-2H03 | Tenants screen (HOST) — per-tenant licensing (S4) | P2 | KPI chips correct | Known tenant mix | 1. Open Tenants; cross-check chips | Cloud tenants count, other companies, Licences OK x/y, devices bound, total evidence storage all match DB
TC-2H04 | Tenants screen (HOST) — per-tenant licensing (S4) | P2 | Slug links open branded consoles | Tenants with slugs | 1. Click /khan link | New tab: admin.smartept.com/khan branded login/console
TC-2H05 | Tenants screen (HOST) — per-tenant licensing (S4) | P1 | Licence pills reflect every state | Tenants in states: active, evaluation, no licence, expired; plus a non-cloud company | 1. Review each row's pill | ACTIVE green; EVALUATION amber with days left; NO LICENCE red; EXPIRED per grace; non-cloud shows INSTALL pill
TC-2H06 | Tenants screen (HOST) — per-tenant licensing (S4) | P2 | Seats column warns when full | Tenant with bound == device_limit | 1. Review seats cell | Rendered amber/bold 'n / n'
TC-2H07 | Tenants screen (HOST) — per-tenant licensing (S4) | P1 | Per-tenant Validate button works | Tenant with stale last check | 1. Click Validate on the row | Phone-home fires for THAT tenant only; button shows result; row refreshes with new last-check time
TC-2H08 | Tenants screen (HOST) — per-tenant licensing (S4) | P3 | Storage cache notice | - | 1. Footer note on Tenants | States 10-minute refresh + billing-lives-in-Central reminder + install licence status
TC-2H09 | Tenants screen (HOST) — per-tenant licensing (S4) | P2 | Validate on non-cloud company rejected cleanly | - | 1. POST /api/tenants/{nonCloudId}/license/validate | 422 'uses the install-level licence — validate it from the Licence screen'
2I. Daily validate command — per-tenant licensing (S4)
TC-2I01 | Daily validate command — per-tenant licensing (S4) | P1 | Command validates install + every tenant row | Install + 2 tenant rows keyed | 1. php artisan smartept:validate-license | One output line per configured row (Install / Tenant #id (name)); each bundle refreshed
TC-2I02 | Daily validate command — per-tenant licensing (S4) | P2 | Exit code fails when any row blocked | One tenant revoked | 1. Run command; echo $? | Non-zero exit; blocked row named in output
TC-2I03 | Daily validate command — per-tenant licensing (S4) | P3 | No keys anywhere → graceful warn | Fresh DB, no keys | 1. Run command | Warning about no key; exit success; nothing crashes
2J. Automated & regression — per-tenant licensing (S4)
TC-2J01 | Automated & regression — per-tenant licensing (S4) | P1 | PerTenantLicenseTest green | Local Laragon | 1. php artisan test --filter=PerTenantLicenseTest | All 5 tests pass
TC-2J02 | Automated & regression — per-tenant licensing (S4) | P1 | M9 licence + M11 offboarding suites green (regression) | - | 1. php artisan test --filter=M9LicenseTest 2. --filter=M11OffboardingTest | All pass unchanged — client-hosted behaviour untouched
TC-2J03 | Automated & regression — per-tenant licensing (S4) | P2 | Full product suite green | - | 1. test.bat | No failures
TC-2J04 | Automated & regression — per-tenant licensing (S4) | P1 | Live smoke after deploy | Steps 3–4 of SR-04 §12 done | 1. /khan web login 2. Khan agent sign-in + sync 3. Tenants screen on live 4. Central tenant storage stats next day | All green; Khan on own licence; per-tenant storage flowing
3A. Migration & automated tests — licence change flows (S5)
TC-3A01 | Migration & automated tests — licence change flows (S5) | P1 | Migration adds renewal_device_limit cleanly | Central at face8e7; local Laragon DB | 1. php artisan migrate 2. DESCRIBE licences | 2026_08_12_000500 runs clean; renewal_device_limit nullable UNSIGNED INT after device_limit; no ENUMs; no data lost
TC-3A02 | Migration & automated tests — licence change flows (S5) | P1 | LicenceChangeFlowsTest green | - | 1. php artisan test --filter=LicenceChangeFlowsTest | All 5 tests pass (incl. the exact ₹10,000 + ₹1,800 GST interpolated-difference case)
TC-3A03 | Migration & automated tests — licence change flows (S5) | P1 | Progressive pricing regression green | - | 1. php artisan test --filter=PerpetualProgressivePricingTest | Full acceptance matrix still passes — the upgrade engine changed nothing in base pricing
TC-3A04 | Migration & automated tests — licence change flows (S5) | P2 | Migration rollback clean | Migration applied | 1. php artisan migrate:rollback --step=1 2. Re-migrate | Column drops and re-adds without error
3B. Admin billed upgrade — cloud subscription — licence change flows (S5)
TC-3B01 | Admin billed upgrade — cloud subscription — licence change flows (S5) | P1 | Upgrade… button appears on active licences only | Licences list with active + suspended + trial rows | 1. Central admin → Licences 2. Compare rows | Active subscription & perpetual rows show Upgrade…; suspended/expired/trial rows do not
TC-3B02 | Admin billed upgrade — cloud subscription — licence change flows (S5) | P1 | Pro-rata order raised with GST paper trail | Active annual cloud subscription, e.g. 25 users, months remaining | 1. Upgrade… → new total 30 → Raise upgrade order | Order number returned; description 'Mid-period upgrade 25 → 30 users — pro-rata for N remaining day(s)'; total = diff/month × remaining months + 18% GST; pay link copyable
TC-3B03 | Admin billed upgrade — cloud subscription — licence change flows (S5) | P1 | Recording payment applies the new limit instantly | Upgrade order from previous case | 1. Billing → the order → Record payment (full) 2. Licences list | Licence shows the new limit; expiry date UNCHANGED; licence History shows upgrade_order + order paid; GST invoice issued in the shared series
TC-3B04 | Admin billed upgrade — cloud subscription — licence change flows (S5) | P2 | Reduction attempt rejected with guidance | Active 30-user subscription | 1. Upgrade… → enter 20 | 422: 'Enter a user count higher than the current 30 — reductions apply at renewal, not mid-period'
TC-3B05 | Admin billed upgrade — cloud subscription — licence change flows (S5) | P2 | Expired-period subscription refused (renew instead) | Subscription past expiry | 1. Upgrade… → any higher count | 422: 'no remaining period — use Renew instead'
3C. Admin billed upgrade — perpetual — licence change flows (S5)
TC-3C01 | Admin billed upgrade — perpetual — licence change flows (S5) | P1 | Exact interpolated difference on example bands | Perpetual licence 15 users; bands 15→₹15k, 30→₹25k configured | 1. Upgrade… on the perpetual row → 30 users → Raise order | Subtotal exactly ₹10,000; GST ₹1,800; total ₹11,800; description 'Lifetime licence upgrade 15 → 30 users — one-time price difference'
TC-3C02 | Admin billed upgrade — perpetual — licence change flows (S5) | P1 | Payment raises limit; AMC re-bases next cycle | Order from previous case | 1. Record payment 2. Later: raise AMC quote for this client | device_limit = 30 immediately; the NEXT AMC quote prices 18% of the 30-user interpolated price (amcQuote reads prevailing count)
TC-3C03 | Admin billed upgrade — perpetual — licence change flows (S5) | P1 | Above priced bands → custom quote, never a price | Bands end at 100 users | 1. Upgrade… → 150 users | 422 custom-quotation message with WhatsApp number; NO order created; ₹0 impossible
TC-3C04 | Admin billed upgrade — perpetual — licence change flows (S5) | P2 | Perpetual reduction rejected | Perpetual 30 users | 1. Upgrade… → 20 | 422: 'a lifetime licence never reduces once purchased'
TC-3C05 | Admin billed upgrade — perpetual — licence change flows (S5) | P2 | Modal wording is kind-aware | - | 1. Open Upgrade… on a subscription, then on a perpetual | Subscription modal explains pro-rata/expiry-unchanged; perpetual modal explains one-time difference + .lic re-issue note
3D. Downgrade-at-renewal — admin side — licence change flows (S5)
TC-3D01 | Downgrade-at-renewal — admin side — licence change flows (S5) | P1 | Edit licence schedules a reduction | Active 40-user subscription | 1. Edit → 'Reduce to (at next renewal)' = 25 → Save 2. Licences list | Saved; row shows amber '↓ 25 at renewal'; History shows licence.edited with renewal_device_limit
TC-3D02 | Downgrade-at-renewal — admin side — licence change flows (S5) | P1 | Guard: not below devices in use | Licence with 10 active devices | 1. Edit → reduction = 5 → Save | 422: 'Scheduled reduction is below the devices currently in use — free seats first'
TC-3D03 | Downgrade-at-renewal — admin side — licence change flows (S5) | P2 | Blank clears the schedule | Schedule set | 1. Edit → clear the field → Save | renewal_device_limit NULL; badge gone
3E. Downgrade-at-renewal — portal + billing — licence change flows (S5)
TC-3E01 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P1 | Portal card schedules a reduction | Client portal login; active 40-user subscription; 3 devices in use | 1. Buy & Renew → 'Reduce users at next renewal' → 25 → Schedule | Toast confirms; card shows 'Scheduled: your next renewal reduces to 25 users'; Cancel button appears; audit client.schedule_reduction
TC-3E02 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P1 | Renewal order bills the REDUCED size | Schedule = 25 on a 40-user licence | 1. Portal → Renew now (or admin raises renewal) 2. Inspect order | Order line priced for 25 devices; description contains '25 devices' + 'scheduled reduction from 40 users applies on payment'; meta apply_device_limit = 25
TC-3E03 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P1 | Payment applies reduction and clears schedule | Renewal order from previous case | 1. Record payment / pay 2. Check licence | device_limit = 25; renewal_device_limit = NULL; expiry extended one period; portal card no longer shows a schedule
TC-3E04 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P2 | Portal guard: not a reduction / below devices in use | 40-user licence, 3 devices in use | 1. Try scheduling 45 2. Try scheduling 2 | 45 → 'That is not a reduction — use the mid-period upgrade'; 2 → 'You currently have 3 device(s) in use…'
TC-3E05 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P2 | Cancel schedule works | Schedule set | 1. Portal card → Cancel schedule | renewal_device_limit NULL; message 'renewals bill your current size again'
TC-3E06 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P2 | Perpetual cannot schedule a reduction | Perpetual licence id | 1. POST client/api/licences/{id}/schedule-reduction devices=10 | 422: 'Only Cloud subscriptions reduce at renewal — a lifetime licence never reduces once purchased'
TC-3E07 | Downgrade-at-renewal — portal + billing — licence change flows (S5) | P3 | Renewal without schedule unchanged (regression) | No schedule | 1. Renew and pay | Billed at current size; limit unchanged; identical to pre-change behaviour
3F. Portal upgrade cards & visibility — licence change flows (S5)
TC-3F01 | Portal upgrade cards & visibility — licence change flows (S5) | P1 | Perpetual tenant sees lifetime upgrade card | Portal login of a perpetual client (active) | 1. Buy & Renew | 'Add users to your lifetime licence' card with one-time-difference wording + never-reduces note; Get upgrade amount & pay works end-to-end via pay page
TC-3F02 | Portal upgrade cards & visibility — licence change flows (S5) | P1 | Cloud tenant still sees pro-rata card (regression) | Active cloud subscription with days remaining | 1. Buy & Renew | 'Add users mid-period (pro-rata)' card exactly as before; payment raises seats instantly
TC-3F03 | Portal upgrade cards & visibility — licence change flows (S5) | P2 | Why-not note replaces silence | Trial tenant portal; then an expired tenant | 1. Buy & Renew on each | Trial: 'Trials upgrade by buying a plan below…'; expired: 'Your licence is expired — renew or contact us…' — never a blank page
TC-3F04 | Portal upgrade cards & visibility — licence change flows (S5) | P2 | Portal upgrade endpoint branches by kind | Perpetual licence via API | 1. POST client/api/licences/{id}/upgrade devices=30 | Order created via createPerpetualUpgradeOrder (description says lifetime price difference), not the pro-rata engine
3G. Self-service .lic re-download — licence change flows (S5)
TC-3G01 | Self-service .lic re-download — licence change flows (S5) | P1 | Bound licence downloads a fresh signed .lic | Client-hosted active licence WITH server_fingerprint; portal login | 1. Portal → Licences → Download licence file (.lic) 2. Import on the product Licence screen | File downloads (correct filename); product imports and activates; bundle carries CURRENT device_limit; audit licence.file_issued by client:<email>
TC-3G02 | Self-service .lic re-download — licence change flows (S5) | P1 | Unbound licence gets guidance, not a file | Client-hosted licence with NO fingerprint | 1. Portal → Licences | Message: 'available once your server has validated online once (or send us its fingerprint…)'; endpoint returns 422 if called directly
TC-3G03 | Self-service .lic re-download — licence change flows (S5) | P1 | Client can NEVER set a new fingerprint | Bound licence | 1. POST client/api/licences/{id}/license-file with a 'fingerprint' body field | Field ignored — file is signed with the STORED fingerprint only; moving machines still requires admin Shift machine
TC-3G04 | Self-service .lic re-download — licence change flows (S5) | P2 | Cloud-deployment client refused politely | Cloud tenant portal | 1. Call the license-file endpoint | 422: 'Licence files are for self-hosted servers — your Cloud console is licensed automatically'
TC-3G05 | Self-service .lic re-download — licence change flows (S5) | P2 | Post-upgrade .lic carries the new seat count | Perpetual client upgraded 15→30 and paid | 1. Re-download .lic 2. Import on server | Product Licence screen shows 25→30-seat entitlement (new device_limit) after import
TC-3G06 | Self-service .lic re-download — licence change flows (S5) | P2 | Cross-tenant access blocked | Two tenants; tenant B's licence id | 1. As tenant A, call license-file / upgrade / schedule-reduction on B's id | 404 on every endpoint (tenant scoping)
TC-3G07 | Self-service .lic re-download — licence change flows (S5) | P3 | Admin Licence file button unchanged (regression) | - | 1. Admin → Licences → Licence file (with and without stored fingerprint) | Behaviour identical to 6-Aug build incl. fingerprint remembering and re-download
3H. Paper trail & money regression — licence change flows (S5)
TC-3H01 | Paper trail & money regression — licence change flows (S5) | P1 | GST invoice issued in the shared series for upgrades | Paid admin upgrade order | 1. Billing → Invoices | Invoice numbered in the single EPT-{FY} series; amounts match order (subtotal/GST/total); appears in client portal invoices
TC-3H02 | Paper trail & money regression — licence change flows (S5) | P1 | History timeline complete | Licence that was upgraded + scheduled + .lic-downloaded | 1. Admin → Licences → History | Timeline shows upgrade_order, order paid, licence.edited (schedule), file_issued (client) — nothing missing
TC-3H03 | Paper trail & money regression — licence change flows (S5) | P2 | USD tenant upgrade converts currency | Tenant with currency USD | 1. Raise an upgrade order | Line converted at usd_inr_rate; GST 0 for USD; '(USD)' suffix on the line
TC-3H04 | Paper trail & money regression — licence change flows (S5) | P2 | Existing flows untouched (Central smoke) | - | 1. php artisan test (full Central suite) or test.bat | FinancialFlowTest, GstInvoiceTest, ClientPortalTest, CentralSmokeTest all green
Fill in: Result (dropdown), Tested By, Date, Notes. Sign-off rule: every P1 = Pass ⇒ the full 11–12 Aug body of work is approved on live. Any P1 = Fail ⇒ STOP and report to Ejaz with the Notes cell filled.

## Summary
Execution Summary — auto-computed from the Test Cases sheet
Metric | Count
Total test cases
Part 1 (sessions 1–3)
Part 2 (per-tenant licensing)
Part 3 (licence change flows)
P1 (must-pass)
P2
P3
Passed
Failed
Blocked
Not tested / blank
Order of execution: Part 1 on LIVE after deploy · Parts 2–3 on local Laragon first, then repeat their P1s on live.